## Bank Collaboration Plan
Date | Task | Priority | Assigned To | Status | Expected Outcome
March 18 | Finalize BOP outreach strategy | High | Syed Wasi | Pending | Defined approach
March 19 | Send email to BOP for meeting | High | Syed Wasi | Pending | Email sent
March 20 | Follow up with BOP, call bank representative | High | Syed Wasi | Pending | Meeting scheduled
March 22 | Prepare pitch deck for BOP meeting | High | Syed Wasi | Pending | Presentation ready
Week 1 |  |  | Outreach strategy finalized, communication initiated, and meeting arranged.
March 25 | Conduct meeting with BOP representatives | High | Syed Wasi | Pending | Initial discussion
March 27 | Negotiate terms and discuss API access | High | Syed Wasi | Pending | API integration approval
Week 2 |  |  | BOP meeting conducted, terms negotiated, and API integration approved
April 2 | Prepare pitch deck for MCB | High | Syed Wasi | Pending | Bank-ready presentation
April 3 | Contact MCB for meeting | High | Syed Wasi | Pending | Meeting scheduled
April 5 | Conduct MCB meeting | High | Syed Wasi | Pending | Initial discussion
Week 3 |  |  | MCB presentation prepared, meeting scheduled, and initial discussion held
April 8 | Follow up with MCB for agreement terms | High | Syed Wasi | Pending | Finalizing details
April 10 | Reach out to Askari Bank | High | Syed Wasi | Pending | Meeting scheduled
April 12 | Prepare pitch for Askari | High | Syed Wasi | Pending | Presentation ready
Week 4 |  |  | MCB follow-up conducted, Askari Bank contacted, and pitch prepared
April 15 | Conduct Askari Bank meeting | High | Syed Wasi | Pending | Agreement discussion
April 18 | Negotiate API integration with Askari | High | Syed Wasi | Pending | API approval
Week 5 |  |  | Engaged with Askari Bank to conduct meeting and negotiate API integration
Partnership Formalized with BOP , MCB and ASKARI Banks
May 1 | Contact UBL for meeting | High | Syed Wasi | Pending | Meeting scheduled
May 3 | Prepare pitch for UBL | High | Syed Wasi | Pending | Presentation ready
Week 6 |  |  | Meeting coordinated with UBL, and pitch deck prepared
May 6 | Conduct UBL meeting | High | Syed Wasi | Pending | Agreement discussion
May 10 | Follow up with UBL, finalize agreement | High | Syed Wasi | Pending | API integration confirmed
Week 7 |  |  | UBL meeting held, follow-up done, and agreement finalized
May 12 | Contact HBL for meeting | High | Syed Wasi | Pending | Meeting scheduled
May 14 | Prepare pitch for HBL | High | Syed Wasi | Pending | Presentation ready
May 18 | Conduct HBL meeting | High | Syed Wasi | Pending | Agreement discussion
Week 8 |  |  | HBL pitch finalized, meeting arranged, and key discussions conducted
May 22 | Finalize API terms with HBL | High | Syed Wasi | Pending | Partnership confirmed
Partnership Formalized with UBL and HBL Banks
June 1 | Reach out to Standard Chartered | High | Syed Wasi | Pending | Meeting scheduled
June 3 | Prepare pitch for Standard Chartered | High | Syed Wasi | Pending | Presentation ready
June 6 | Conduct Standard Chartered meeting | High | Syed Wasi | Pending | Agreement discussion
Week 9 |  |  | Engaged with Standard Chartered, pitch finalized, and meeting conducted
June 10 | Follow up and finalize API agreement | High | Syed Wasi | Pending | API integration confirmed
June 12 | Reach out to Faysal Bank | High | Syed Wasi | Pending | Meeting scheduled
June 14 | Prepare pitch for Faysal Bank | High | Syed Wasi | Pending | Presentation ready
Week 10 |  |  | API finalized, Faysal Bank contacted, pitch prepared
June 17 | Conduct Faysal Bank meeting, finalize deal | High | Syed Wasi | Pending | Final bank onboarded
Partnership Formalized with Standard Chartered and Faysal Banks